# DevNorth 2026 — Project Brief

Approved planning baseline · 13 August 2026

# Outcome

Run DevNorth 2026 as a sold-out, well-rated one-day developer conference on 18 September 2026 for 450 attendees. Success means at least 405 checked-in attendees, an average satisfaction score of 4.4/5, and sponsor revenue of PKR 12,000,000.

# Scope and constraints

Venue: Expo Centre Lahore, Hall B; contracted capacity 500.

Programme: three tracks, 18 sessions, one keynote, and an evening networking reception.

Budget ceiling: PKR 28,000,000 with a 10% contingency reserve.

Registration closes 11 September 2026; final catering count is due 12 September.

Wi-Fi must support 450 concurrent devices with a tested failover connection.

# Delivery plan

| Deliverable | Owner | Due | Acceptance evidence |
| --- | --- | --- | --- |
| Venue readiness | Aisha Khan | 05 Sep | Capacity and failover test signed by venue manager |
| Registration operations | Omar Siddiqui | 11 Sep | 405+ confirmed attendees and QR check-in rehearsal |
| Programme readiness | Sara Ali | 09 Sep | All speakers confirmed; backup keynote brief approved |
| Sponsor delivery | Bilal Ahmed | 12 Sep | PKR 12m contracted and sponsor inventory reconciled |

# Outcome checkpoints

Checkpoint 1 — 28 August: confirm venue capacity and tested network failover. Checkpoint 2 — 11 September: confirm 405 registrations, all speaker backups, and sponsor revenue. If either checkpoint fails, the executive sponsor will reduce programme scope or move to the backup venue.