## Schedule
DevNorth 2026 — Delivery Schedule & Resourcing
Workstream | Owner | Start | Due | Status | Budget PKR | Evidence
Venue & network | Aisha Khan | 2026-08-20 | 2026-09-05 | On track | 4200000 | 500-device failover test
Registration | Omar Siddiqui | 2026-08-15 | 2026-09-11 | On track | 1800000 | 405 confirmed attendees
Programme | Sara Ali | 2026-08-12 | 2026-09-09 | At risk | 6500000 | 18 speakers + backup keynote
Sponsors | Bilal Ahmed | 2026-08-10 | 2026-09-12 | On track | 2800000 | PKR 12m contracted
Event operations | Hina Raza | 2026-09-01 | 2026-09-18 | Not started | 8700000 | Run-of-show rehearsal
Total delivery budget |  |  |  |  | 24000000